## PROJECT OVERVIEW
Key | Value | Status | Notes
Project Name | YR Interiors & Furnitures | DONE | High-end architectural interior design and furniture website
Client | Thanu Gowda | DONE | Client and business owner
Technical Director / Lead Developer | Mohammed Sab (Dvoper / InitWave Technologies) | DONE | Full-stack architecture & creative technology direction
Current Environment | DEV / UAT | DONE | Successfully pushed to DEV and UAT branches on GitHub
Current Branch | dev / uat (main pending client approval) | IN PROGRESS | Code ready for final main merge upon client sign-off
Framework | Next.js 14/15 (App Router) | DONE | Server and Client components with static generation
Language | TypeScript | DONE | Type-safe interfaces across data and components
Styling System | Tailwind CSS | DONE | Custom luxury dark theme (#1c1b1a, #121211, warm alabaster)
Animation Technology | GSAP (GreenSock) + ScrollTrigger | DONE | Cinematic Sketch-to-Reality SVG loader and micro-interactions
Hosting Status | Pending Vercel Configuration | PENDING | To be linked after main branch merge
Domain Status | Pending GoDaddy DNS Setup | PENDING | A and CNAME records to be configured post-Vercel setup
Client Review Status | Under Review / UAT Ready | IN PROGRESS | Preview video and UAT branch ready for final client sign-off

## COMPLETE PROJECT STRUCTURE
Category | File/Folder | Full Path | Purpose | Type | Important? | Can Developer Modify? | Notes
App | layout.tsx | src/app/layout.tsx | Root layout, metadata, global providers, injected PageLoader and CookieConsent | Layout | Yes | Yes | Controls global HTML shell and SEO metadata
App | page.tsx | src/app/page.tsx | Homepage composition (Hero, About, Services, FeaturedProjects, Footer) | Page | Yes | Yes | Main landing page with JSON-LD structured data
App | projects/[slug]/page.tsx | src/app/projects/[slug]/page.tsx | Dynamic case study detail pages with masonry gallery and next-project loop | Dynamic Page | Yes | Yes | Utilizes generateStaticParams for optimal edge caching
App | projects/[slug]/loading.tsx | src/app/projects/[slug]/loading.tsx | Instant routing feedback state during case study transitions | Loading State | Yes | Yes | Provides immediate visual response on click
App | privacy-policy/page.tsx | src/app/privacy-policy/page.tsx | India-compliant privacy policy legal page | Legal Page | Yes | Yes | Drafted for IT Act 2000 compliance
App | terms/page.tsx | src/app/terms/page.tsx | India-compliant terms and conditions legal page | Legal Page | Yes | Yes | Governs interior design services and jurisdiction
Components | PageLoader.tsx | src/components/PageLoader.tsx | Cinematic Sketch-to-Reality GSAP loader with color reveal and 8px blur melt | Component | Yes | Yes | Executes on initial load and hydration
Components | CookieConsent.tsx | src/components/CookieConsent.tsx | GDPR and India-compliant cookie consent banner | Component | Yes | Yes | Stores user preference in localStorage
Components | Header.tsx | src/components/Header.tsx | Global navigation bar with smooth anchor links | Component | Yes | Yes | Fixed translucent header
Components | Hero.tsx | src/components/Hero.tsx | Full-bleed cinematic hero with WhatsApp CTA | Component | Yes | Yes | LCP element with priority image loading
Components | About.tsx | src/components/About.tsx | Studio philosophy and editorial introduction | Component | Yes | Yes | Typography-driven layout
Components | Services.tsx | src/components/Services.tsx | Architectural and interior services breakdown | Component | Yes | Yes | Numbered luxury list format
Components | FeaturedProjects.tsx | src/components/FeaturedProjects.tsx | Homepage masonry project showcase with full-color hover zoom | Component | Yes | Yes | Links to dynamic project routes
Components | Footer.tsx | src/components/Footer.tsx | Elite dark-theme footer with floating newsletter card and social SVG icons | Component | Yes | Yes | Includes InitWave credit and legal links
Data | projects.ts | src/data/projects.ts | Centralized project case study data repository | Data Store | Yes | Yes | Add/edit projects here
Data | services.ts | src/data/services.ts | Centralized studio services data repository | Data Store | Yes | Yes | Add/edit services here
Public Assets | hero-interior.jpg | public/hero-interior.jpg | Primary hero background imagery | Image | Yes | Yes | High-res interior render
Public Assets | project-1.png | public/project-1.png | Featured project 1 & newsletter thumbnail | Image | Yes | Yes | Full color display

## WEBSITE PAGES & SECTIONS
Page | Route | Section | Component/File | Purpose | Content Source | Editable Location | Status | Notes
Homepage | / | Cinematic Loader | PageLoader.tsx | Initial architectural sketch reveal | Inline SVG | src/components/PageLoader.tsx | IMPLEMENTED | GSAP powered
Homepage | / | Header | Header.tsx | Main navigation and brand logo | Hard-coded / Props | src/components/Header.tsx | IMPLEMENTED | Fixed position
Homepage | / | Hero | Hero.tsx | Full-bleed introductory banner | Hard-coded | src/components/Hero.tsx | IMPLEMENTED | WhatsApp & Consultation CTAs
Homepage | / | About Studio | About.tsx | Studio philosophy statement | Hard-coded | src/components/About.tsx | IMPLEMENTED | Editorial typography
Homepage | / | Services | Services.tsx | List of core interior services | src/data/services.ts | src/data/services.ts | IMPLEMENTED | Data-driven items
Homepage | / | Featured Works | FeaturedProjects.tsx | Selected architectural projects | src/data/projects.ts | src/data/projects.ts | IMPLEMENTED | Full-color zoom hover
Homepage | / | Newsletter CTA | Footer.tsx | Floating subscription card | Interactive State | src/components/Footer.tsx | IMPLEMENTED | Functional email capture
Homepage | / | Footer | Footer.tsx | Multi-column enterprise footer | Hard-coded | src/components/Footer.tsx | IMPLEMENTED | Includes InitWave credit
Project Detail | /projects/[slug] | Case Study View | src/app/projects/[slug]/page.tsx | Detailed project showcase | src/data/projects.ts | src/data/projects.ts | IMPLEMENTED | Dynamic routing
Privacy Policy | /privacy-policy | Legal Content | src/app/privacy-policy/page.tsx | India IT Act compliant privacy policy | Hard-coded | src/app/privacy-policy/page.tsx | IMPLEMENTED | Dedicated route
Terms & Conditions | /terms | Legal Content | src/app/terms/page.tsx | Interior design terms of service | Hard-coded | src/app/terms/page.tsx | IMPLEMENTED | Dedicated route

## IMAGE & MEDIA ASSET MAP
Asset Name | Asset Type | Current File Name | Full Path | Used On | Section | Component | How It Is Imported | Where To Replace | Recommended Replacement Format | Dimensions if known | Notes
Hero Interior 1 | Image | hero-interior.jpg | public/hero-interior.jpg | Homepage | Hero | Hero.tsx | Static public path | Replace public/hero-interior.jpg | JPG / WebP (1920x1080px) | 1920x1080 | LCP optimized
Hero Interior 2 | Image | hero-interior-2.jpg | public/hero-interior-2.jpg | Homepage | Hero / Background | Hero.tsx | Static public path | Replace public/hero-interior-2.jpg | JPG / WebP | 1920x1080 | Secondary background image
Hero Interior 3 | Image | hero-interior-3.jpg | public/hero-interior-3.jpg | Homepage | Hero / Background | Hero.tsx | Static public path | Replace public/hero-interior-3.jpg | JPG / WebP | 1920x1080 | Tertiary background image
About Interior | Image | about-interior.png | public/about-interior.png | Homepage | About | About.tsx | Static public path | Replace public/about-interior.png | PNG / WebP | 1200x800 | Studio philosophy visual
Project 1 | Image | project-1.png | public/project-1.png | Homepage & Footer | Featured Works / Newsletter | FeaturedProjects.tsx & Footer.tsx | Static public path | Replace public/project-1.png | PNG / WebP | 1200x800 | Also used as newsletter thumbnail
Project 2 | Image | project-2.png | public/project-2.png | Homepage & Projects | Featured Works | FeaturedProjects.tsx | Static public path | Replace public/project-2.png | PNG / WebP | 1200x800 | Full color display
Project 3 | Image | project-3.png | public/project-3.png | Homepage & Projects | Featured Works | FeaturedProjects.tsx | Static public path | Replace public/project-3.png | PNG / WebP | 1200x800 | Full color display
Placeholder SVG | SVG | placeholder.svg | public/placeholder.svg | Various | Fallback | Multiple | Static public path | Replace public/placeholder.svg | SVG | Scalable | Fallback graphic

## TEXT & CONTENT MANAGEMENT
Content | Page | Section | Current Text/Identifier | File | Exact Location/Component | Editable? | How To Change | Notes
Hero Heading | Homepage | Hero | DESIGNING SPACES. CREATING COMFORT. | Hero.tsx | src/components/Hero.tsx | Yes | Edit text inside src/components/Hero.tsx | Primary value proposition
Hero Subtitle | Homepage | Hero | Transform your space with thoughtfully designed interiors... | Hero.tsx | src/components/Hero.tsx | Yes | Edit paragraph in src/components/Hero.tsx | Subheading
Studio Philosophy | Homepage | About | We believe that a well-designed space... | About.tsx | src/components/About.tsx | Yes | Edit text in src/components/About.tsx | Brand narrative
Services List | Homepage | Services | Residential Interiors, Commercial Interiors... | services.ts | src/data/services.ts | Yes | Edit objects in src/data/services.ts | Centralized data array
Projects Data | Homepage & Dynamic | Featured Works | The Alabaster Residence, Nexus Corporate HQ... | projects.ts | src/data/projects.ts | Yes | Edit objects in src/data/projects.ts | Powers dynamic routing
Footer Copyright | Global | Footer | © 2026 YR Interiors & Furnitures. All rights reserved. | Footer.tsx | src/components/Footer.tsx | Yes | Edit src/components/Footer.tsx | Automatic year

## NAVIGATION & LINKS
Link Label | Location | Component/File | Current Destination | Link Type | Status | Where To Change | Notes
Studio | Header & Footer | Header.tsx / Footer.tsx | /#studio | Internal Anchor | IMPLEMENTED | Header.tsx & Footer.tsx | Smooth scroll
Projects | Header & Footer | Header.tsx / Footer.tsx | /#projects | Internal Anchor | IMPLEMENTED | Header.tsx & Footer.tsx | Smooth scroll
Services | Header & Footer | Header.tsx / Footer.tsx | /#services | Internal Anchor | IMPLEMENTED | Header.tsx & Footer.tsx | Smooth scroll
Contact | Header & Footer | Header.tsx / Footer.tsx | /#contact | Internal Anchor | IMPLEMENTED | Header.tsx & Footer.tsx | Smooth scroll
Get a Free Consultation | Hero & Footer | Hero.tsx / Footer.tsx | #contact | Action CTA | IMPLEMENTED | Hero.tsx / Footer.tsx | Primary CTA
WhatsApp Us | Hero & Footer | Hero.tsx / Footer.tsx | https://wa.me/916361464303 | External Link | IMPLEMENTED | Hero.tsx / Footer.tsx | Direct chat link
Privacy Policy | Footer & Cookie Consent | Footer.tsx / CookieConsent.tsx | /privacy-policy | Internal Route | IMPLEMENTED | Footer.tsx | Legal page
Terms & Conditions | Footer | Footer.tsx | /terms | Internal Route | IMPLEMENTED | Footer.tsx | Legal page
InitWave Technologies | Footer | Footer.tsx | https://initwave.in/ | External Link | IMPLEMENTED | Footer.tsx | Developer credit

## SOCIAL MEDIA LINKS
Platform | Current URL | Location | Component | File | Status | Correct URL Required | Where To Update | Appears In | Notes
Instagram | # | Footer | Footer.tsx | src/components/Footer.tsx | PENDING — CLIENT URL REQUIRED | Yes | src/components/Footer.tsx | Footer social icons | Placeholder link
Facebook | # | Footer | Footer.tsx | src/components/Footer.tsx | PENDING — CLIENT URL REQUIRED | Yes | src/components/Footer.tsx | Footer social icons | Placeholder link
WhatsApp | https://wa.me/916361464303 | Hero & Footer | Hero.tsx & Footer.tsx | Multiple | IMPLEMENTED | Yes | Hero.tsx & Footer.tsx | Hero CTA & Footer social | Active WhatsApp link
LinkedIn | # | Footer | Footer.tsx | src/components/Footer.tsx | PENDING — CLIENT URL REQUIRED | Yes | src/components/Footer.tsx | Footer social icons | Placeholder link

## EMAIL & CONTACT CONFIGURATION
Purpose | Current Email | Location | File | Component/API | Environment Variable | Status | Where To Change | Client Input Required? | Notes
Official Client Email | hello@yrinteriors.com | Footer & Contact | Footer.tsx | Footer.tsx | None (Hardcoded) | IMPLEMENTED | src/components/Footer.tsx | No | Official business email
Newsletter Subscription | Interactive Form | Footer Newsletter Card | Footer.tsx | Footer.tsx (useState handler) | None | IMPLEMENTED | src/components/Footer.tsx | No | Frontend success state active

## PHONE & WHATSAPP DETAILS
Contact Type | Current Value | Location | File | Component | Status | Where To Change | Notes
Phone / WhatsApp Number | +91 6361464303 | Hero & Footer | Multiple files | Hero.tsx, Footer.tsx | IMPLEMENTED | Hero.tsx and Footer.tsx | Official business contact
Studio Address | No.15, 3rd cross, Kasthuriba nagar, Ashwathkatte road, Bangalore 560026 | Footer | Footer.tsx | Footer.tsx | IMPLEMENTED | src/components/Footer.tsx | Physical studio location

## SEO
SEO Element | Page | Current Value | File | Location | Editable? | Where To Change | Status | Notes
Page Title | Homepage | YR Interiors & Furnitures ¦ Premium Interior Design | layout.tsx | src/app/layout.tsx | Yes | src/app/layout.tsx metadata | IMPLEMENTED | Optimized title
Meta Description | Homepage | Crafting deeply personal spaces with architectural precision since 2012. | layout.tsx | src/app/layout.tsx | Yes | src/app/layout.tsx metadata | IMPLEMENTED | Meta description
Open Graph | Homepage | Configured for social sharing | layout.tsx | src/app/layout.tsx | Yes | src/app/layout.tsx | IMPLEMENTED | OG metadata active
Structured Data (Schema) | Homepage | HomeAndConstructionBusiness JSON-LD | page.tsx | src/app/page.tsx | Yes | src/app/page.tsx | IMPLEMENTED | Local business schema

## ANIMATIONS & INTERACTIONS
Animation | Page/Section | Technology | Component/File | Trigger | Behaviour | Duration | Editable Location | Performance Notes
Sketch to Reality Loader | Initial Load | GSAP + SVG | PageLoader.tsx | Window load / Hydration | Draws SVG lines, color reveal, scale 115% & 8px blur melt | ~3.5s total | src/components/PageLoader.tsx | GPU accelerated, unmounts on complete
Smooth Scrolling | Global | CSS | globals.css | Anchor clicks | Smooth scroll behavior | Native CSS | src/app/globals.css | Lightweight
Gallery Zoom Hover | Featured Works | Tailwind CSS | FeaturedProjects.tsx | Mouse enter | Smooth scale up on full-color images | 700ms | src/components/FeaturedProjects.tsx | CSS transform

## 3D - WEBGL - SPECIAL EFFECTS
Effect | Technology | Component | File | Asset | Purpose | Editable Parameters | Performance Considerations | Mobile Behaviour | Notes
SVG Architectural Path Animation | SVG strokeDasharray + GSAP | PageLoader | PageLoader.tsx | Inline SVG | Cinematic room sketch drawing effect | Stroke width, duration, easing | Zero heavy WebGL overhead, highly performant | Fully responsive viewBox | Awwwards-level entry effect

## FORMS & FUNCTIONALITY
Feature | Page | Component | File | Input Fields | Submission Method | Backend/API | Destination | Status | Where To Modify | Notes
Newsletter Subscription | Homepage Footer | Footer | Footer.tsx | Email Address | React useState handler | Frontend state success message | Client state | IMPLEMENTED | src/components/Footer.tsx | Interactive confirmation
Cookie Consent Banner | Global | CookieConsent | CookieConsent.tsx | Accept / Reject buttons | localStorage | Client localStorage | Browser storage | IMPLEMENTED | src/components/CookieConsent.tsx | India IT Act / GDPR compliant

## ENVIRONMENT VARIABLES
Variable Name | Purpose | Used In | Required For | DEV Required? | Production Required? | Where Configured | Notes
SECRET — DO NOT INCLUDE VALUE | Placeholder for future backend integrations | None currently required | Future API hooks | No | No | .env.local (when needed) | No secrets currently exposed in codebase

## DEPENDENCIES
Package | Version | Purpose | Used For | Critical? | Can Remove? | Notes
next | 14/15 | Core React Framework | App router, SSR, routing | Yes | No | Production ready
react / react-dom | 18+ | UI Library | Component rendering | Yes | No | Core dependency
tailwindcss | 3+ | Styling | Utility-first design | Yes | No | Configured with custom theme
gsap | Latest | Animation Engine | PageLoader cinematic animations | Yes | No | High performance

## DEPLOYMENT CHECKLIST
Step | Task | Responsible | Status | Required Input | Where To Configure | Verification Method | Notes
1 | DEV Branch Push | Developer | DONE | Git repository | Local terminal | GitHub commit check | Successfully pushed
2 | UAT Branch Push & Preview | Developer & Client | DONE / UNDER REVIEW | Client feedback | GitHub UAT branch | Vercel Preview URL | Ready for final client sign-off
3 | Merge DEV to MAIN | Developer | PENDING CLIENT APPROVAL | Client approval | GitHub repository | Git merge main | Awaiting client sign-off
4 | Vercel Production Setup | Developer | PENDING MAIN MERGE | Vercel account connection | Vercel Dashboard | Vercel deployment logs | Auto-links to main branch
5 | GoDaddy Domain DNS Configuration | Client & Developer | PENDING VERCEL SETUP | GoDaddy credentials / DNS values | GoDaddy Domain Manager | Live domain SSL check | Pointing A & CNAME records to Vercel

## PENDING ITEMS
ID | Item | Category | Current Status | Priority | Client Input Required? | Developer Action | Exact Location | Dependency | Before Production? | Notes
PEND-01 | Client final review and approval of UAT build | Client Review | PENDING | High | Yes | Wait for client sign-off | UAT Preview | Required before Main merge | Yes | Video preview and UAT link provided
PEND-02 | Social media URLs (Instagram, Facebook, LinkedIn) | Content | PENDING | Medium | Yes | Update Footer.tsx with real URLs | src/components/Footer.tsx | None | Recommended | Currently set to placeholder links
PEND-03 | Merge dev/uat to main branch | Deployment | PENDING | High | No | Execute git merge main | Git repository | PEND-01 | Yes | Ready upon approval
PEND-04 | Vercel production deployment & GoDaddy DNS | Deployment | PENDING | High | Yes (DNS access) | Configure Vercel project and DNS records | Vercel & GoDaddy | PEND-03 | Yes | Final launch step

## CHANGE MANAGEMENT GUIDE
Question | Answer / Exact Location | Status
Where do I change the hero image? | Replace public/hero-interior.jpg, public/hero-interior-2.jpg, or edit src/components/Hero.tsx | DONE
Where do I change project images? | Replace files in public/ or edit project objects in src/data/projects.ts | DONE
Where do I change the logo / brand name? | src/components/Header.tsx and src/components/Footer.tsx | DONE
Where do I change social media URLs? | src/components/Footer.tsx (social icon href attributes) | DONE
Where do I change the official email? | src/components/Footer.tsx (hello@yrinteriors.com) | DONE
Where do I change phone/WhatsApp number? | src/components/Hero.tsx and src/components/Footer.tsx (+91 6361464303) | DONE
Where do I change navigation links? | src/components/Header.tsx and src/components/Footer.tsx | DONE
Where do I change footer content? | src/components/Footer.tsx | DONE
Where do I change SEO title and meta description? | src/app/layout.tsx metadata export | DONE
Where do I modify the cinematic loader? | src/components/PageLoader.tsx (GSAP timelines and SVG paths) | DONE
How do I add a new project case study? | Add a new object to the projects array in src/data/projects.ts and place asset in public/ | DONE
How do I run the project locally? | npm install followed by npm run dev | DONE
How do I create a production build? | npm run build followed by npm start | DONE

## DESIGN SYSTEM
Token Category | Token Name | Value | Usage
Color | Background Dark | #1c1b1a / #121211 | Footer, Loader, Dark Sections
Color | Warm Alabaster | #F9F8F6 | Primary light backgrounds and text
Typography | Heading Font | Serif (Playfair Display / Editorial Serif) | Headings and brand titles
Typography | Body Font | Inter / Sans-serif | Paragraphs and navigation
Spacing | Container Padding | px-6 lg:px-20 | Global layout margins
Border | Subtle Hairline | border-white/10 | Dividers and card borders

## FINAL HANDOVER SUMMARY
Section | Details
Completed | Full editorial frontend architecture, GSAP Sketch-to-Reality loader, dynamic project routing, full-color gallery hover zoom, India-compliant legal pages (/privacy-policy, /terms), GDPR/India cookie consent banner, multi-column enterprise footer with newsletter state and social SVG icons.
Pending | Final client sign-off on UAT preview, merge to main branch, Vercel production deployment, GoDaddy DNS configuration.
Client Input Required | Final approval of UAT build, social media URLs (Instagram, Facebook, LinkedIn), GoDaddy domain/DNS access credentials.
Developer Action Required | Merge dev/uat to main upon approval, configure Vercel production project, point GoDaddy DNS records to Vercel.
Production Configuration Required | Vercel custom domain setup (yrinteriors.com), SSL verification, DNS propagation.
Handover Readiness | YES — Fully documented, tested locally, and structured for immediate handover and deployment.

## DEVELOPER SETUP (15A)
Step / Category | Item | Requirement | Command / Action | Notes
1. Runtime | Node.js | v18.x or v20.x LTS | node -v | Required for Next.js 14/15 runtime
2. Package Manager | npm | v9+ | npm install | Verified package manager
3. Clone Repository | Git Clone | Git installed | git clone https://github.com/Mohammadsabn/yr-interiors.git | Clones repository locally
4. Checkout Branch | Branch Switching | dev or uat branch | git checkout dev | Switch to active development branch
5. Install Dependencies | npm install | package.json | npm install | Installs all dependencies
6. Local Development | Run Dev Server | Next.js dev script | npm run dev | Starts local server at http://localhost:3000
7. Production Build | Build Script | Next.js build script | npm run build | Creates optimized production bundle
8. Production Start | Start Script | Next.js start script | npm start | Runs production server locally